## Sprints
Sprint | Week | Sprint Goal | Start Date | End Date | Sprint State
1 | 2/3 |  | 2024-10-24 | 2024-11-08 | Inactive
2 | 4/5 | Discuss project flow. Part Distrubution between group members. | 2024-11-07 | 2024-11-18 | Closed
3 | 6/7 | Start working on respective features of each member: ● Main function (Customer and admin log in) ● Security feautre ● Environmental Control ( Moisture, temperature and humidity sensors) ● Payment feature | 2024-11-21 | 2024-12-02 | Closed
MST + Term Break
4 | 13 | Start working on the website for drinks order. Features to implement includes: ● Customer sign in with phone number ● Display the drinks menu ● Processing payment ● Sending QR code via telegram to the phone number entered to collect drinks | 2025-01-06 | 2025-01-10 | Closed
5 | 14 | Add drinks and inventories to database. The website is able to display drinks menu. If Customer is selected in main menu, direct to selecting drinks via keypad and integrate LCD menu. Implement functions: ● Simulating Preparing drink ● Simulating Inventory check | 2025-01-13 | 2025-01-17 | Closed
6 | 15/16 | Implement hardware: ● Testing RFID scanner ● Testing camera Implement payment methods ( RFID, QR or Barcode), and after payment confirm order. Implement receiveing QR code from telegram for drinks collection. | 2025-01-20 | 2025-01-31 | Closed
7 | 17 | Implement hardware: ● Testing servo motor ● Testing IR sensor Implement admin log-in function in main menu ● Entering password to open door Implement security features ● Check whether the door is forcefully opened ● Taking video footage and send to admin team via telegram | 2025-02-03 | 07 February 2025 | Closed
8 | 18 | Implement hardware: ● Testing moisture sensor, temp & humidity sensor Implement environment monitoring feature ● Monitor sensors and send to admin team via telegram if control fails Combining parts and debugging | 2025-02-10 | 2025-02-14 | Closed
9 | 18/19 | ● Final debugging ●Container Deployment ●Python test cases ●Update and edit documents, Demonstration | 2025-02-17 | 2025-02-21 | Active
Formulas:
Start Date = [Start Date, row above]+14
End Date = [Start Date]+11

## Active Sprint Board (hidden)
To Do | Doing | Done

## Product Backlog
ID | Story Title | Story Description | Definition of Done | Estimated Effort (hours) | Actual Effort (hours) | Status | Sprint
1 | Create Use Case Diagrams in SRS document | As a Software Developer, I need to define all the different Use Case Diagrams for the Automated Checkout System | All necessary Use Case Diagrams are defined in the SRS document SRS document is commited and pushed to Github | 4 | 5 | To Do | Sprint 1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95 | [5 empty] | Doing
96
97
98
99
100

## enum (hidden)
Sprint | Start Date | End Date | Story Status | Spint State
Sprint 1 |  |  | To Do | Inactive
Sprint 2 |  |  | Doing | Active
Sprint 3 |  |  | Done | Closed
Sprint 4
Sprint 5
Sprint 6